## Fall
Phases | Done? | Sub phases | Week | F22 | [16 empty] | Winter Break |  |  | S23
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
|  |  |  | 8/29/22 - 9/4/22 | 9/5/22 - 9/11/22 | 9/12/22 - 9/18/22 | 9/19/22 - 9/25/22 | 9/26/22 - 10/2/22 | 10/3/22 - 10/9/22 | 10/10/22 - 10/16/22 | 10/17/22 - 10/23/22 | 10/24/22 - 10/30/22 | 10/31/22 - 11/6/22 | 11/7/22 - 11/13/22 | 11/14/22 - 11/20/22 | 11/21/22 - 11/27/22 | 11/28/22 - 12/4/22 | 12/5/22 - 12/11/22 | 12/12/22 - 12/18/22 | 12/19/22 - 12/25/22 | 12/26/22 - 1/1/23 | 1/2/23 - 1/1/8/22 | 1/9/22 - 1/15/22 | 1/16/22 - 1/22/22 | 1/23/22 - 1/29/22 | 1/30/22 - 2/5/22 | 2/6/22 - 2/12/22 | 2/13/22 - 2/19/22 | 2/20/22 - 2/26/22 | 2/27/22 - 3/5/22 | 3/6/22 - 3/12/22 | 3/13/22 - 3/19/22 | 3/20/22 - 3/26//22 | 3/27/22 - 4/2/22 | 4/3/22 - 4/9/22 | 4/10/22 - 4/16/22 | 4/17/22 - 4/23/22 | 4/24/22 - 4/30/22 | 5/1/22 - 5/7/22 | 5/8/22 - 5/14/22
Planning |  | Define overall project goal | TRUE | bar: F22 1 to F22 2
|  | Decide on research topics | FALSE | bar: F22 1 to F22 2
|  | Finalize general timeline | FALSE | bar: F22 1 to F22 2
|  | Make a funding plan, Jira | FALSE | bar: F22 2
|  | Discuss professor involvement | FALSE | bar: F22 1 to F22 2
Finish Prototype |  | order new electronics | FALSE | bar: F22 2 to F22 6
|  | make a pcb | FALSE | bar: F22 2 to F22 6
|  | launch, test, and review | FALSE | bar: F22 4 to F22 6
Research |  |  | FALSE | bar: F22 5 to F22 6
Ideate |  |  | FALSE | bar: F22 5 to F22 6
Sketch and CAD |  |  | FALSE | bar: F22 5 to F22 8
Design Review w/ Bedillion |  |  | FALSE | bar: F22 8
Parts Acquisition |  |  | FALSE | bar: F22 7 to F22 9
Fabrication |  |  | FALSE | bar: F22 7 to F22 11
Assembly |  |  | FALSE | bar: F22 9 to F22 11
Testing |  |  | FALSE | bar: F22 12 to F22 15
Record Data |  |  | FALSE | bar: F22 13 to F22 15
Ideate #2 |  |  | FALSE | bar: F22 16 to F22 17
Design Iteration |  |  | FALSE | bar: Winter Break 18 to S23 21
Design Review |  |  | FALSE | bar: Winter Break 20 to S23 21
Parts Acquisition |  |  | FALSE | bar: S23 22 to S23 24
Fabrication |  |  | FALSE | bar: S23 22 to S23 24
Assembly |  |  | FALSE
Testing |  |  | FALSE
Record Data |  |  | FALSE
Thesis Report |  |  | FALSE
Presentation |  |  | FALSE
Publish? |  |  | FALSE

## Spring
Phases | Done? | Sub phases | Week | F22 | [16 empty] | Winter Break |  |  | S23
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
|  |  |  | 8/29/22 - 9/4/22 | 9/5/22 - 9/11/22 | 9/12/22 - 9/18/22 | 9/19/22 - 9/25/22 | 9/26/22 - 10/2/22 | 10/3/22 - 10/9/22 | 10/10/22 - 10/16/22 | 10/17/22 - 10/23/22 | 10/24/22 - 10/30/22 | 10/31/22 - 11/6/22 | 11/7/22 - 11/13/22 | 11/14/22 - 11/20/22 | 11/21/22 - 11/27/22 | 11/28/22 - 12/4/22 | 12/5/22 - 12/11/22 | 12/12/22 - 12/18/22 | 12/19/22 - 12/25/22 | 12/26/22 - 1/1/23 | 1/2/23 - 1/1/8/22 | 1/9/22 - 1/15/22 | 1/16/22 - 1/22/22 | 1/23/22 - 1/29/22 | 1/30/22 - 2/5/22 | 2/6/22 - 2/12/22 | 2/13/22 - 2/19/22 | 2/20/22 - 2/26/22 | 2/27/22 - 3/5/22 | 3/6/22 - 3/12/22 | 3/13/22 - 3/19/22 | 3/20/22 - 3/26//22 | 3/27/22 - 4/2/22 | 4/3/22 - 4/9/22 | 4/10/22 - 4/16/22 | 4/17/22 - 4/23/22 | 4/24/22 - 4/30/22 | 5/1/22 - 5/7/22 | 5/8/22 - 5/14/22
Planning |  | Define overall project goal | TRUE | bar: F22 1 to F22 2
|  | Decide on research topics | FALSE | bar: F22 1 to F22 2
|  | Finalize general timeline | FALSE | bar: F22 1 to F22 2
|  | Make a funding plan, Jira | FALSE | bar: F22 2
|  | Discuss professor involvement | FALSE | bar: F22 1 to F22 2
Finish Prototype |  | order new electronics | FALSE | bar: F22 2 to F22 6
|  | make a pcb | FALSE | bar: F22 2 to F22 6
|  | launch, test, and review | FALSE | bar: F22 4 to F22 6
Research |  |  | FALSE | bar: F22 5 to F22 6
Ideate |  |  | FALSE | bar: F22 5 to F22 6
Sketch and CAD |  |  | FALSE | bar: F22 5 to F22 8
Design Review w/ Bedillion |  |  | FALSE | bar: F22 8
Parts Acquisition |  |  | FALSE | bar: F22 7 to F22 9
Fabrication |  |  | FALSE | bar: F22 7 to F22 11
Assembly |  |  | FALSE | bar: F22 9 to F22 11
Testing |  |  | FALSE | bar: F22 12 to F22 15
Record Data |  |  | FALSE | bar: F22 13 to F22 15
Ideate #2 |  |  | FALSE | bar: F22 16 to F22 17
Define research objectives and think about how to present at the end | TRUE | bar: Winter Break 18 to S23 21
Assemble the Test Rig | TRUE | Fabricate rings (3d print), | bar: S23 22
Assemble the Test Rig | TRUE | drill out rings mount encoders, | bar: S23 22
Assemble the Test Rig | TRUE | create encoder pieces | bar: S23 22
Assemble the Test Rig | TRUE | mount ring system to test rig | bar: S23 22
Assemble the Test Rig | TRUE | figure out second encoder mounting | bar: S23 22
Parachute Deployment Design | TRUE | Sketch out design ideas | bar: S23 22
Parachute Deployment Design | FALSE | Test drag with sim or drop test | bar: S23 22
Parachute Deployment Design | FALSE | begin CAD for design | bar: S23 22
Parachute Deployment Design | FALSE | order new tube
New Rocket | FALSE | find gimbal design to modify
New Rocket | FALSE | complete gimbal CAD and 3D print
New Rocket | FALSE | test and mount gimbal
New Rocket | FALSE | New PCB? could just make a servo board
New Rocket | FALSE | If new PCB needed order all parts needed and new PCB
New Rocket | FALSE | complete full rocket cad design before cutting tube
New Rocket | FALSE | Design and 3D print new electronics bay
New Rocket | FALSE
FALSE
FALSE
FALSE